Andwell Health Partners

Home-Based Primary Care Implementation Roadmap

Prepared by: Home Centered Care Institute

Guiding Principles

- Core Components of HCCI’s Practice Implementation Model:

  - Business Plan & Financials

  - Human Capital Management

  - Clinical Care

  - Operations

  - Technology & Infrastructure

  - Quality

  - Marketing & Growth

  - Legal & Compliance

- Andwell Health Partners’ Current State Highlights:

  - Strong palliative and wound care programs

  - Six board-certified hospice/palliative physicians, 8–9 NPs

  - Financial sustainability challenges; need alternative payment models

  - Rural service area with geographic and telehealth reimbursement barriers

  - Previous RPM program discontinued due to cost, but is now being externalized

  - Commitment to community outreach and quality metrics

Phase 1

Strategic Planning & Grant Proposal Development

Objectives:

- Build a business plan and grant proposal for funders and stakeholders.

- Define HBPC scope and financial model.

Key Actions:

- Business Plan & Financials:

  - Develop cost projections for HBPC (startup costs: training, staffing, travel, technology; operational costs: employee salaries, travel, telehealth infrastructure).

  - Estimate potential savings using Medicare analysis and HBPC benchmarks.

  - Model alternative payment strategies (shared savings, ACO partnerships, risk-based contracts).

  - Estimate annual costs (to be calculated based on staffing and visit volume)

- Human Capital Management:

  - Define Staffing Model (NP-driven model with physician oversight)

  - Design support staffing model

- Clinical Care:

  - Define patient eligibility criteria and care pathways.

  - Consider additional care models

    - Longitudinal HBPC with CCM

    - TCM

    - Telehealth

- Operations:

  - Assess geographic coverage and routing logistics

  - Discuss strategies to minimize expenses during startup operations

- Technology & Infrastructure:

  - Assess current EHR capabilities and gaps for HBPC

  - Define documentation, scheduling, and mobile access needs

  - Identify telehealth requirements and potential costs

  - Assess data reporting and analytics capabilities

- Quality:

  - Consider operationalization: metrics (hospitalizations, ED visits, patient and caregiver satisfaction).

  - Plan for causal impact analysis (per Confer Analytics® Market Analysis).

- Marketing & Growth:

  - Develop marketing plan to outline proforma

- Legal & Compliance:

  - Review Maine state regulations for HBPC and telehealth.

  - Ensure compliance with CMS billing and documentation standards.

  - Draft policies for HIPAA, patient consent, and home visit protocols.

Issues & Risk Mitigation

- Financial viability/sustainability

  - Evaluate and incorporate APMs

- Geographic and telehealth barriers

  - Discuss assisted telehealth services with MA or other as well as limiting geographic range

- State-specific regulatory constraints on home-based care

  - Conduct regulatory review for Maine (Andwell Health Partners)

- Start/Anti-Kickback risks with internal referrals

  - Incorporate compliance oversight and legal review into organizational design

Deliverables:

- Market Needs Assessment Summary

- Defined HBPC Model

- Staffing & Operating Model

- 2-5 Year Pro Forma & Financial Model

- Risk & Mitigation Assessment

Phase 2

Pilot Program Design & Infrastructure

Objectives:

- Build operational framework and prepare for pilot.

Key Actions:

- Business Plan & Financials:

  - Operationalize the approved business plan and proforma

  - Validate financial assumptions in a real-world pilot

  - Establish financial reporting and performance monitoring

- Human Capital Management:

  - Draft job descriptions and recruitment plan.

  - Evaluate scalability and workforce risks (burnout, travel burden, coverage gaps)

- Clinical Care:

  - Consider operationalization: clinical policies and procedures for HBPC and integration with palliative and wound care programs.

- Operations:

  - Map end-to-end patient journey (referral, onboarding, ongoing care)

  - Define coordination workflows with internal service lines (map integration points)

  - Establish baseline operational KPI’s

  - Address rural logistics (travel optimization, telemedicine).

- Technology & Infrastructure:

  - Select EMR enhancements for HBPC documentation.

- Quality:

  - Ensure clinical quality, safety, and regulatory compliance

- Marketing & Growth:

  - Consider operationalization: payer engagement; negotiation strategy outline

  - Prepare evidence package (cost savings, qualitative data).

- Legal & Compliance:

  - Finalize compliance programs for coding and documentation.

  - Conduct staff training on legal requirements and risk management.

Deliverables:

- Fully operational HBPC pilot program

- Pilot performance dashboards (clinical, financial, operational)

Issues & Risk Mitigation

- Workforce Readiness & Capacity

  - Implement structured onboarding with competency checklists, conduct pre-pilot workflow simulations, and minimize travel burden using routing tools and defined geographic service zones

- Operational Workflow Reliability

  - Conduct tabletop tests of workflows, develop standardized SOPs across the care continuum, and hold weekly operational huddles to identify issues early, and support rapid‑cycle improvements.

- Technology & EMR Readiness

  - Finalize HBPC documentation templates and mobile access features before pilot launch